## About
About this workbook
Enter milestone and task information in the Milestones and Tasks worksheets. To chart milestones along the timeline, enter 0 in the no. column, then, update the label position to be "below" to avoid overlapping labels. The position column in the milestone table, charts milestones within the task chart either on the same row or in stacked rows. To chart them on the same row, enter the same number in this column for each milestone. To chart them on different rows, enter different numbers. Sample data charts all milestones along the row position of 2.
Guide for screen readers
There are 5 worksheets in this workbook: About Milestones Tasks Gantt Chart Dynamic Chart Data (Hidden) The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
Dynamic Chart Data (Hidden)
Do not delete or modify content in the Hidden worksheet. Doing so could compromise the integrity of the Gantt Charting. Data may appear blank, dates may appear to be incorrect, do not fill in, edit, delete or otherwise modify the data or you risk overwriting formulas and breaking the chart graphing capability. The DynamicMilestone table allows for 15 milestones to be charted. To chart more than 15, simply expand the table to accommodate your number. Remember, only add the actual milestone data in the Chart Data worksheet.
Tips
By default, milestones are charted on row 1 of the Gantt Chart using the Position column in the Chart Data worksheet, starting in cell C5. To chart milestones on different rows, simply change the number.
The default setting is to highlight today's date in the Gantt Chart. To no longer highlight Today's date, simply select "no" in the Chart Data worksheet in cell D2.
The Gantt Chart date timeline is charted with a gap of 5 dates between them. To change this, select the timeline in the Gantt Chart worksheet and select Format Axis. Change the Major unit from 5 to 1 or 10, for example.
This is the last instruction in this worksheet.

## Milestones
Create a Date Tracking Gantt Chart in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Date tracking Gantt chart
Select option Yes in cell D2 if you want to highlight today's date in the Gantt Chart worksheet. Select option No in cell D2 if you do not want to highlight today's date in the Gantt Chart worksheet. In Cell D2, select ALT+Arrow Down for options. | Track today's date? |  | No
Milestones header for the milestone table is in cell B3. Tasks header for the tasks table is in cell G3. | Milestones
Information about the columns in the milestone table are in this row from cells B4 through E4. Information about the columns in the tasks table are in this row from cells G4 through J4. | This column should be ordered sequentially. | The position column, charts milestones within the task chart. | Enter the date for a milestone in this column. | Enter a milestone description in this column. These descriptions will appear in the chart.
Milestone table headers are in cells B5 through E5. Tasks table headers are in cells G5 through J5. Milestone sample data is in cells B6 through E11. Tasks sample data is in cells G6 through J17. The next instruction is in cell A21. | No. | Position | Date | Milestone
| 1 | 6 | 2025-05-14 | Zakończenie Fazy Projektowej
| 2 | 3 | 2025-05-24 | Ukończenie Warstwy Danych i Logiki
| 3 | 1 | 2025-06-04 | Wersja "testowa" z Funkcjonalnym GUI
| 4 | 6 | 2025-06-07 | Zakończenie Implementacji
| 5 | 5 | 2025-06-14 | Projekt Gotowy do Złożenia
To add more Milestones, add a new row above this one. Note, the default number of milestones to chart is 15. Adding new milestones requires a change in the hidden worksheet. See the About worksheet cell A9 for more information. The next instruction is in cell A26. | To add more Milestones, add a new row above this one.
A note is in cell G26. This is the last instruction in this worksheet.

## Tasks
Create a Date Tracking Gantt Chart in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Date tracking Gantt chart
Milestones header for the milestone table is in cell B3. Tasks header for the tasks table is in cell G3. | Tasks
| This column should be ordered sequentially. | Enter the start date for each task below. For best results sort this column in ascending order. | Enter the end date for each task or activity below, in this column. | Enter tasks and/or activities in this column. | Auto calculated column used for charting the duration of each task. Do not delete or modify.
| No. | Start Date | End Date | Task | Duration in days
| 1 | 2025-05-10 | 2025-05-12 | Specyfikacja Wymagań Systemowych | 3
| 2 | 2025-05-13 | 2025-05-14 | Projektowanie Schematu Bazy Danych | 2
| 3 | 2025-05-15 | 2025-05-19 | Implementacja Klas Modelu | 5
| 4 | 2025-05-20 | 2025-05-24 | Implementacja Warstwy Dostępu do Danych (DAO) | 5
| 5 | 2025-05-25 | 2025-05-31 | Budowa Głównych Okien i Formularzy GUI | 7
| 6 | 2025-05-30 | 2025-06-04 | Implementacja Logiki Obsługi Zdarzeń | 6
| 7 | 2025-06-05 | 2025-06-07 | Stylizacja Interfejsu i Poprawa Użyteczności | 3
| 8 | 2025-06-08 | 2025-06-10 | Testowanie Manualne Scenariuszy Użytkownika | 3
| 9 | 2025-06-09 | 2025-06-15 | Kontrola Wersji (finalne commity) | 7
| 10 | 2025-06-10 | 2025-06-14 | Przygotowanie Dokumentacji Technicznej (finalizacja) | 5
To add more Tasks, add a new row above this one.

## Gantt Chart
Gantt Chart showing Today, milestones and tasks within a date range is in this worksheet. A scrollbar is in row 1 from cells B1 through R1 and increments the date range showing future milestones. The chart is drawn within cells B2 through R3. This is the last instruction in this worksheet.

## Dynamic Chart Data Hidden (hidden)
Title of this worksheet is in cell B1. | Dynamic Chart data, Do NOT edit or delete this worksheet!
Table title is in cells B2 and C2. | Today | highlight |  |  |  | Charting range
Table heading is in cells B3 and C3. These coordinates create the Today highlight in the chart. The first column marks the day, the second indicates to draw the line that highlights today. The first column date may change so the chart date range stays readable as the dates progress, however, a y co-ord of 0 indicates no line is drawn. Do not modify or delete this content or the charting may break. To no longer highlight Today's date, simply select "no" in the Chart Data worksheet in cell D2. The next instruction is in cell A7. | today highlight x co-ord | y co-ord |  |  |  | 2025-05-10
| 2025-06-12 | 0 |  |  |  | 2025-05-25
| 2025-06-12 | 0 |  |  |  | 2025-06-12
| 2025-06-12 | 0 |  |  |  | 2025-06-12
Table heading is in cell B7. The scrolling increment in cell B8 represents the data graphed and visually appearing in the Gantt Chart at any one time. Scrolling with the scroll bar at the top of the chart in row 1 of the Gantt Chart worksheet, will increment this number. The charting works best with single increments. The next instructin is in cell A10. | 2025-06-12 | 0 |  |  |  | 2025-06-12
| 2025-06-12 | 0 |  |  |  | 2025-06-12
| 2025-06-12 | 0 |  |  |  | 2025-06-12
Table heading is in cell B10 and D10. The Charting Range helps select the appropriate range of tasks and milestones. Do not modify these fields. The ageoff number, keeps the chart readable by aging tasks from the range and only plotting those that are within the range. Do not modify this number. The next instruction is in cell A14. |  |  | ageoff |  |  | 2025-06-12
|  |  | 45 |  |  | 2025-06-12
Table heading for Dynamic Milestone Data is in cells B14 through E14. A note is in cell F14. This table creates the Gantt Chart in the Gantt Chart worksheet, plotting 7 milestones at a time. The data in this chart is auto generated based on the content in the table above. Do not edit or delete this table or its contents. The next instruction is in cell A17. |  |  |  |  | <-- this table creates the gantt chart, plotting 7 milestones at a time
| scroll increment |  |  |  |  | Milestone charting
Cells G15 trhrough I15 contain table headings for Dynamic Milestone Data. Data in this table may appear blank, dates may appear to be incorrect, do not fill in, edit, delete or otherwise modify this data or you risk overwriting formulas and breaking the chart graphing capability. The table allows for 15 milestones to be charted. To chart more than 15, simply expand the table to accommodate your number. Remember, only add the milestones in the Chart Data worksheet. Do not add any content to this table. A note is in cell J15. The next insruction is in cell A32. | 0 |  |  |  |  | Milestones | Date | Baseline | <-- this table creates the milestone markers in the gantt chart, plotting only those milestones that fit in the range of dates shown; up to 15 milestones
[6 empty] | Zakończenie Fazy Projektowej | 2025-05-14 | 6
[6 empty] | Ukończenie Warstwy Danych i Logiki | 2025-05-24 | 3
[6 empty] | Wersja "Testowa" z Funkcjonalnym GUI | 2025-06-04 | 1
[6 empty] | Zakończenie Implementacji | 2025-06-07 | 6
[6 empty] | Projekt Gotowy do Złożenia | 2025-06-14 | 5
2025-05-25
2025-05-25
2025-05-25
2025-05-25
| Tasks | Start date | Task duration in days | position |  |  | 2025-05-25
| Specyfikacja Wymagań Systemowych | 2025-05-10 | 3 | 10 |  |  | 2025-05-25
| Projektowanie Schematu Bazy Danych | 2025-05-13 | 2 | 9 |  |  | 2025-05-25
| Implementacja Klas Modelu | 2025-05-15 | 5 | 8 |  |  | 2025-05-25
| Implementacja Warstwy Dostępu do Danych (DAO) | 2025-05-20 | 5 | 7 |  |  | 2025-05-25
A note is in cell J32. This is the last instruction in this worksheet. | Budowa Głównych Okien i Formularzy GUI | 2025-05-25 | 7 | 6 |  |  | 2025-05-25 |  | <--To chart more than 15 milestones, simply expand this table and enter new entries in the Milestone table in the Chart Data worksheet.
| Implementacja Logiki Obsługi Zdarzeń | 2025-05-30 | 6 | 5 |  |  | 2025-05-25
| Stylizacja Interfejsu i Poprawa Użyteczności | 2025-06-05 | 3 | 4 |  |  | 2025-05-25
| Testowanie Manualne Scenariuszy Użytkownika | 2025-06-08 | 3 | 3 |  |  | 2025-05-25
| Kontrola Wersji (finalne commity) | 2025-06-09 | 7 | 2 |  |  | 2025-05-25
| Przygotowanie Dokumentacji Technicznej (finalizacja) | 2025-06-10 | 5 | 1 |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0 |  |  |  | 2025-05-25
|  | 2025-05-10 | 0
|  | 2025-05-10 | 0
|  | 2025-05-10 | 0
|  | 2025-05-10 | 0
|  | 2025-05-10 | 0